## Sheet1
Sprint Retrospective
Liked | Learned | Lacked | Longed For
Share aspects of the sprint that you enjoyed or found particularly effective. | Discuss lessons learned, whether they are related to processes, technical aspects, or teamwork. | Identify areas where the team felt a lack of resources, support, or information. | Discuss any desires or expectations that the team had but were not met during the sprint. | Guidelines
The team showed excellent coordination, especially with the data collection module, which led to smooth and timely completion of the task. | We Early testing showed the importance of validating datasets for both quality and diversity to improve accuracy in the model. | Clear criteria for segmentation validation were missing, causing delays in iterations with radiologists. | A better integration process for radiologist feedback to speed up validation cycles. | Develop a checklist for data validation before segmentation